## Time_table
Working Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Calendar Weeks | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Start of the week | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09
End of the week | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15
Perception working package | 2021-11-28: Documentation on the given guides and projects. Chose main languages and technologies Create/adapt time table Members tasks asignation; 2021-12-05: Lane detection; 2022-05-15: BFMC
Intersection detection
Traffic sign detection
Object detection & classification
Traffic light detection
Position fusion
Other functionalities and optimization
Control working packages | 2021-12-05: Lane keeping
Intersection navigation
Simple action taking maneuvers (brake, acceleration, parking)
Complex action taking maneuvers (switch lane, react to traffic lights, overtake static car, road search)
Safety measures (Emergency brake road search, speed control on ramp)
Other functionalities and optimization
System integration working packages | 2021-12-05: High-level Software arhitecture
Decision making package (strategies, priorities)
GPS reading
Cars interaction
Smart Traffic lights interaction
Path planning
Other functionalities and optimization
Final result & Demo | 2021-11-28: Team can control the car remotely; 2021-12-05: Robot can keep a lane, can make a curve
Robot can recognise an intersection and make a turn
Robot can go on a pre-determined path, stop at stop sign, park at parking sign, slow at crosswalk
Robot can react to dynamic elements while going on a pre-determined path(stop for pedestrian, overtake a static car, park on empty parking spot)
While detecting and calculating it's position, the robot can plan dynamicaly go on a path, react tot raffic lights, send environemt data)
The car should have all funcionalities ready
Progress Reports | 2021-12-12: 1st report - 19th dec.; 2021-12-26: Christmas break; 2022-01-16: 2nd report - 23rd ian.; 2022-02-20: 3rd report - 20th feb.; 2022-03-20: 4th rep and Qualifications - 20th Mar.; 2022-04-17: 5th report 24th apr.; 2022-05-15: Finals 12-16 may.